STEPS AND THE WORK SCHEDULE

for the OFFICE RELOCATION PROJECT

THE STEPS

1. Note the project’s completion date – this is your deadline

2. Estimate the duration for each task in the schedule below – days or hours

3. Total your tasks’ durations and decide on a project commencement date that will enable your project to finish on time.

4. Register for a free Viewpath.com account.

5. Access your Viewpath account and create a project e.g.’OFFICE RELOCATION’. 
NOTE THAT YOU CREATE A TEAM FIRST – THIS INITIATES YOUR PROJECT AND THEN YOU CREATE SUB PROJECTS WITHIN THE PROJECT – refer to the PowerPoint tutorial for instructions on how to use Viewpath and note also that Viewpath has a number of ‘Quick Tips’ videos.

6. Create a project for each of the project’s sub projects.

7. Enter the tasks and their durations for each sub project. Do not enter the start and finish dates – this can be adjusted later.

8. Select all sub projects and tasks and click the ‘links’ icon to establish dependencies between tasks – Note your Gantt chart

9. You can click on a task’s box in the Gantt chart and adjust the position of the task to change its start date.

NOTE THAT YOUR VIEWPATH SCHEDULE IS AUTOMATICALLY SAVED.

THE SCHEDULE

Sub project 1 – Prepare for the relocation

| TASK | DURATION |
| --- | --- |
| Review all office systems-what to keep, what to sell. |  |
| Prepare inventory furniture and equipment. |  |
| Order new phone and fax numbers. |  |
| Order carpets |  |
| Order window coverings or drapes. Order new furniture |  |
| Order any new audio visual equipment for conference, and meeting areas. |  |
| Order new telecommunications equipment. Select, hire and schedule moving company |  |

Sub Project 2 – Organise the relocation

| TASK | DURATION |
| --- | --- |
| Clean out office items which should not be moved. |  |
| Arrange for disposal of furniture and equipment not being moved. Begin preparation of change of address announcements. |  |
| Develop time schedules for staff relocation |  |
| Evaluate server and network needs |  |
| Engage cleaning crew to remove packing and clean up damage after move. |  |
| Engage a plant service to deliver and maintain plants. |  |
| Prepare and hand out a set of "Move Guidelines." |  |
| Review all plans with the moving company and building managers. |  |
| Remove all personal items from old office. |  |

Sub Project 3 – Other relocation tasks

| TASK | DURATION |
| --- | --- |
| Install new telecommunications equipment and office technology. |  |
| Mail change of address notices and send out client announcements |  |
| Select and install artwork. |  |

Sub Project 4 – Relocation training for staff

| TASK | DURATION |
| --- | --- |
| Schedule phone and security training |  |
| Schedule ergonomic training for new furniture. |  |
| Schedule new technology training. |  |